## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | AI-Powered Knowlegde Engine for smart support &Ticket Resolution | MUST HAVE | Non | All | 3- Completed
S1 | S1 | US-001 | Development of GUI | MUST HAVE | Streamlit | Bipeen Raj | 3- Completed
S1 | S1 | US-001 | Development of Backend Part | MUST HAVE | Non | Bipeen Raj | 3- Completed
S1 | S1 | US-001 | Model Fine Tuning and Integration of Models | MUST HAVE | all-MiniLM-L6-v2,Other Python lib. | Rudra Kadel | 3- Completed
S1 | S1 | US-001 | For training the model and the Datasets | MUST HAVE | Non | Rudra Kadel | 3- Completed
S2 | S2 | US-002 | Introduction of Real-time Recommendation of solution tickets | MUST HAVE | Non | Bipeen Raj | 3- Completed
S2 | S2 | US-002 | Creation of Datasets for the real time recommendation | MUST HAVE | Web and Ai models | Bipeen Raj | 3- Completed
S2 | S2 | US-002 | GUI area for real time solution | MUST HAVE | Streamlit | Bipeen Raj | 3- Completed
S2 | S2 | US-002 | Training model for real time solution | MUST HAVE | Python Lib | Bipeen Raj | 3- Completed
S3 | S3 | US-003 | Introduction of Contact Gap Analysis | MUST HAVE | Non | Bipeen Raj | 3- Completed
S3 | S3 | US-003 | Backened Setup for the log file Creation and use cases | MUST HAVE | Non | Bipeen Raj | 3- Completed
S3 | S3 | US-003 | GUI for Contact Gap Analysis with visualization | MUST HAVE | Metaplotlib,Seaborn,Plotly | Bipeen Raj | 3- Completed
S4 | S4 | US-004 | Introduction to sprint 4 Slack integration and analytics | MUST HAVE | Non | Bipeen Raj | 2- In Progress
S4 | S4 | US-004 | Slack integration to the back-end to contact with GUI | MUST HAVE | Slack channel | Bipeen Raj | 2- In Progress
S4 | S4 | US-004 | Improvement of GUI with notification with the Slack | MUST HAVE | Non | Bipeen Raj | 2- In Progress
S4 | S4 | US-004 | Improvement of GUI with Analytics Button to have visible track of tickets | MUST HAVE | Plotly | Bipeen Raj | 2- In Progress
S4 | S4 | US-004 | Final Training and discussion of the model | MUST HAVE | Non | Bipeen Raj | 2- In Progress
Note on F1: ====== ID#AAABv7in4hw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours |  | AI summary
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 64 | 34 | 21 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction Of Project. Overview and Detailing of Tasks | 2025-10-09 | 2025-10-09 | Bipeen Raj | Others | 3-Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Discussion on GUI and Back-end development and team assign | 2025-10-11 | 2025-10-12 | All Member | Build | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Development of GUI and Basic Back-end | 2025-10-13 | 2025-10-16 | Rudra Kadel | Coding | 3-Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Planning for the next improvement in GUI and how to develop full Backend | 2025-10-17 | 2025-10-17 | Rudra Kadel | Others | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Development of full GUI And Back-end | 2025-10-18 | 2025-10-20 | All Member | Others | 3-Completed | 5 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Fine Tuning and Model Integration | 2025-10-21 | 2025-10-22 | Bipeen Raj | Integration Test | 3-Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Model Trainig | 2025-10-23 | 2025-10-23 | Rudra Kadel | Coding | 3-Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 8 | Introduction to real time solution recommendation | 2025-10-27 | 2025-10-27 | All Member | Others | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 9 | Development of Back-end for realtime solution recommendation | 2025-10-29 | 2025-10-31 | Bipeen Raj | Coding | 3-Completed | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 10 | Dataset for the real time solution | 2025-10-29 | 2025-10-31 | Bipeen Raj | Build | 3-Completed | 7 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 11 | Gui updated for the real-time Solution with a particular button | 2025-10-31 | 2025-11-01 | Bipeen Raj | Design | 3-Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 12 | Model training Over the new Datasets | 2025-11-01 | 2025-11-02 | Bipeen Raj | System Test | 3-Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 13 | Introduction to Content Gap Analysis Part | 2025-11-01 | 2025-11-03 | Bipeen Raj | Others | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 14 | Development of Backend to manage Log file and keep the log of each ticket | 2025-11-04 | 2025-11-05 | Bipeen Raj | Coding | 3-Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 11 | Gui updated for the Content Gap Data and Visualization | 2025-11-04 | 2025-11-07 | Bipeen Raj | Design | 3-Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 12 | Introduced to Slack integration and the analytics Part | 2025-11-07 | 2025-11-07 | Bipeen Raj | Others | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 13 | Backend setup for Slack integration | 2025-11-08 | 2025-11-10 | Bipeen Raj | Coding | 3-Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 14 | Screen optimization for real time changes | 2025-11-09 | 2025-11-10 | Bipeen Raj | Design | 3-Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 15 | Gui updated (notification button for slack message) | 2025-11-11 | 2025-11-13 | Bipeen Raj | Design | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 16 | Gui updated (Analytic part for Ticket issue visualization) | 2025-11-12 | 2025-11-13 | Bipeen Raj | Design | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 17 | Final Training Of the model and Dataset Updates | 2025-11-14 | 2025-11-16 | Bipeen Raj | System Test | 3-Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABv8H7Dw0 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABv7in4hs Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABv7in4h8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABv7in4iI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABv8H7Dw8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABv7in4iE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABv7in4iM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABv7in4iY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABv7in4hk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABv8H7DxA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABv7in4iA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABv7in4ho Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABv8H7Dw4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABv7in4h0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABv7in4iU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABv7in4iQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABv7in4h4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on how to proceed for the real time recommendation | Conducted detailed discussion with mentor and got confirmation.
Sprint 2 | Day 5 | Too much scope about API integration | Approached my team lead and got a clarity on few things (scope).
Sprint 3 | Day 7 | Lack of clarity on data set for real time recommendation | Discussed with mentor and got a clarity on the data sets to choose from some web.
Sprint 4 | Day 9 | Lack of clarity on stream-lit | Discussed with mentor and got a clarity on the stream-lit tool.
Sprint 5 | Day 14 | Lack of clarity on Real Time Solution Recommendation | Discussed with mentor and have a clear approach.
Sprint 6 | Day 16 | Too much scope on Contact Gap Analysis | Approached my team lead and reduced the scope.
Sprint 7 | Day 18 | Too much scope for Backed setup of log file and use case | Discussed with mentor and reduced the scope.
Sprint 8 | Day 19 | No proper guidance about the Content Gap Analysis implementation. | Discussed with mentor and got guidance to have a clear approach.
Sprint 9 | Day 20 | Less data available for Contact Gap Analysis | Discussed with mentor and found some data source.
Sprint 10 | Day 24 | Not able to connect the backend to frontend with GUI | Discussed with mentor and fixed the issue with some guidance
Sprint 11 | Day 25 | Not able to clear doubts about the frontend notification integration with slack | Asked a few questions to my mentor, she practically gave me a better understanding.
Sprint 12 | Day 27 | Time to do the demo for the presentation for the final training | Discussed with mentor and fixed the time.
Sprint 13 | Day 28 | Less time to prepare for the final presentation | Discussed with mentor and got guidance on how to manage the time.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-10-13 | 2025-10-17 | Bipeen Raj | Documenting data preprocessing steps and embedding configuration | Skipping validation of dataset quality before processing | Leading technical implementation and code reviews | Successfully implemented sentence-transformers embeddings and automated priority classification logic for 234 tickets
2 | Sprint 1 | 2025-10-13 | 2025-10-17 | Laxmi Parsanna | Breaking down presentation content into clear logical sections | Assuming all technical details are understood by non-technical audience | Collaborating on manual tagging sessions and team discussions | Created engaging presentation deck explaining embeddings and priority classification methodology
3 | Sprint 1 | 2025-10-13 | 2025-10-17 | Lahari | Preparing visual aids and diagrams for complex concepts | Delaying preparation until last minute | Active participation in priority classification sessions | Contributed to successful group presentation with clear visual explanations of ticket categorization
4 | Sprint 1 | 2025-10-14 | 2025-10-17 | Bipeen Raj | Asking clarifying questions during requirement discussions | Waiting too long before seeking help on unclear tasks | Maintaining regular communication with team and mentor | Established strong foundation in embeddings and NLP concepts that enabled independent work in Sprint 2
5 | Sprint 2 | 2025-10-17 | 2025-11-05 | Rudra Kadel | Using batch processing and performance optimization techniques | Building systems without benchmarking and testing incrementally | Consulting official documentation and community resources when stuck | Successfully implemented FAISS vector search with Ollama LLM integration achieving real-time recommendation capabilities
6 | Sprint 3 | 2025-11-05 | 2025-11-13 | Rudra Kadel | Implementing caching strategies and state management best practices | Ignoring scalability concerns in initial implementations | Modular code structure with comprehensive error handling | Deployed production-ready Streamlit application with analytics dashboard and Slack integration completing all 35 tasks on schedule
7 | Sprint 4 | 2025-11-13 | 2025-11-17 | Bipeen Raj | Learning about Slack integration | Revising about slack | Learning and practising how to integrate slack | completed the project with this integration